## Progress
WBS | Milestone |  |  | Plan |  | Progress
1 | Inisiasi |  |  | 25% | 25% | 15%
1.1 |  | Kickoff |  |  | 5% | 100%
1.2 |  | Form User Requirement |  |  | 5% | 100%
1.3 |  | Business Process |  |  | 5% | 100%
1.4 |  | Role Matrix |  |  | 5% | 0%
1.5 |  | Entity Relationship Diagram |  |  | 5% | 0%
60%
2 | Development |  |  | 60% | 60% | 60%
Preparation
|  |  | Local |  | 5% | 100%
|  |  | Server |  | 5% | 100%
|  |  | Database |  | 5% | 100%
|  | Frontend Aplikasi |  |  | 20% | 100%
|  | Backend Aplikasi |  |  | 23% | 100%
|  | Deployment |  |  | 2% | 100%
100%
3 | Quality & Performance |  |  | 10% | 10% | 10%
|  | Self Integration Test |  |  | 2% | 100%
|  | User Aceptance Test |  |  | 2% | 100%
|  | Sidang Skripsi |  |  | 6% | 100%
100%
4 | Closing |  |  | 5% | 5% | 0.625%
|  | Documentation |  |  | 2% | 25%
|  | ….. |  |  | 3% | 0%
12.5%
|  |  |  | 100% |  | 85.62%